## Project Plan
Medical Imagery Diagnosis using HPCC platform
| Status |  | Notes | Effort Hours | Begin Date | End Date
Image Procurement & Labeling
|  | Image procurement | Target 40,000 images | 32 | 2022-05-16 | 2022-05-20
|  | Image labeling |  | 40 | 2022-05-23 | 2022-05-27
Prepare training dataset
|  | Validate bias | Will reach to Emory/OSF for Bias documentation
HPCC setup
Local HPCC Thor setup
Run a sample GNN using ECL
Image Feature Extraction
Write a model
Develop a model
Error correction
|  | Hypothesis testing | https://apple.github.io/ml-hierarchical-confusion-matrix
Develop precision recall accuracy
Model Output
Neural Network Model Documentation
Research paper
Predicitive Tree Model
|  | Choose model type | RF, GB, XGB
Choose predicitive attributres
Determine weightages
Develop model
Train model
Error correction
Hypothesis Tesing
Develop precision recall accuracy
Model Output
Tree Model Documentation
Research paper
Research Conclusion
|  | Review of results | Confusion Matrix?
Documentation
Final Documentation
Poster project presentation
Powerpoint presentation
Research Paper
Patent
|  | File a Provisional Patent | If applicable for the HPCC Community